# SCT Off-Detector Electronics Requirements from Schedule V10 21/11/02

## As interpreted by Janet

- Barrel Systems

- Final System

| Barrel Number | Number of Modules | Minimum Number of RODs+BOCs |
| --- | --- | --- |
| 3 | 384 | 8 |
| 4 | 480 | 10 |
| 5 | 576 | 12 |
| 6 | 672 | 14 |

| Item | Number (excluding spares) |
| --- | --- |
| RODs+BOCs | 44 |
| TIMs | 4 |
| Crates+Backplanes | 4 |
| SBCs | 4 |

This is designed to 11 RODs/Crate – the physical maximum is 16 RODs/Crate.

- Build-up during Barrel Macro-Assembly

The supply flow below is intended to show the latest dates consistent with the schedule for the availability of components.

| Event | Date | # Requirement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Oxford |  | KEK |  | CERN |  |
|  |  | RODBOC | New Crate | RODBOC | New Crate | RODBOC | New Crate |
| ### Get going | 1st January 2003 | 1 |  |  |  |  |  |
|  | 15th February 2003 | 1 |  |  |  | 1 |  |
|  | 15th April 2003 |  |  | 1 | 1 |  |  |
| ### Ready for B3 | 15th April 2003 | 3 |  |  |  |  |  |
|  | 15th July 2003 | 4 | 1 |  |  | 1 | 1 |
|  | 30th September 2003 |  |  |  |  | 6 |  |
| ### Ready for B6 | 1st November 2003 | 6 |  |  |  |  |  |
|  | 1st January 2004 |  |  |  |  | 6 |  |
| ### Ready for B5 | 1st September 2003 |  |  | 1 |  |  |  |
|  | 1st January 2004 |  |  | 11 |  |  |  |
| ### Ready for B4 | Nothing new |  |  |  |  |  |  |
| ### Totals |  | 15 | 1 | 13 | 1 | 14 | 1 |

- Endcap Systems

- Final System

The final system, including both endcaps, is planned to consist of up to 48 RODs+BOCs (exact number still under review), situated in 4 crates.  Details of the routing arrangements still to be finalised, I believe.

Total number of endcap modules in final system = 1976 (42 fully-packed RODs+BOCs)

2.2	Build-up during Endcap Macro-Assembly

The supply flow below is intended to show the latest dates consistent with the schedule for the availability of components.

| Event | Date | # Requirement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Liverpool |  | Nikhef |  | CERN |  |
|  |  | RODBOC | New Crate | RODBOC | New Crate | RODBOC | New Crate |
| ### Get going | 15th April 2003 | 1 | 1 |  |  |  |  |
|  | 15th July 2003 | 1 | 1 | 1 | 1 |  |  |
| Ready for Assembly/ | 1st September 2003 | 2 |  | 1 |  |  |  |
| Testing | 1st January 2004 | 3 |  | 2 |  |  |  |
|  | 30th April 2004 |  |  |  |  | 5 | 1 |
| ### Totals |  | 7 | 2 | 4 | 1 | 5 | 1 |

- Schedule for Off-Detector Components

3.1	Crates, Backplanes and TIMs

| #### Date | Number | Comment |
| --- | --- | --- |
| 15th April 2003 | 2 | Crates ordered |
| 15th July 2003 | 4 | Crates reserved from Loan Pool |
| 30th April 2004 | 6 | Crates ordered Nov 2003, phase out Loan Pool crates |
| 30th April 2005 | Spare crates (2?) | Final crate order Nov 2004 |
| #### Total SCT | 8 + spares |  |

Note:  The SBCs will not be supplied by the off-detector budget during the macro-assembly phase, as this is too early to buy the final ATLAS SBCs.

3.2	RODs + BOCs

##### N.B. These must be BOCs fully equipped with opto

| #### Date | Number | Cumulative Series | Comment |
| --- | --- | --- | --- |
| 1st January 2003 | 1 |  | Non-series BOC & ROD |
| 15th February 2003 | 2 | (? 2 RODs | Non-series BOCs, RODs may be final |
| 15th April 2003 | 5 | ? 7 RODs) | Non-series BOCs, RODs may be final |
| 15th July 2003 | 7 | 7 | Series production |
| 1st September 2003 | 10 | 17 |  |
| 1st November 2003 | 6 | 23 |  |
| 1st January 2004 | 22 | 45 |  |
| 30th April 2004 | 5 | 50 |  |
| 30th April 2005 | 42 + spares | 92 + spares | Total ready, start installation in ATLAS |
| #### Total SCT |  | 92 + spares |  |