Off Detector Electronics Status  (May 29, 2002)

High level concerns:

1. The current supply of optical components will only support one partially loaded (12 ch tran and 12 ch rec) BOC.

2. The information needed to design the converter card from the existing optical module connectors to the new connectors is not available.

3. The PC board design of the final BOC can not start until the optical safety design and pin assignment of the optical modules are complete.

4. The availability of optical modules is not known.

5. The level of effort on the DAQ and user evaluation may have detrimental effects on the production schedule for RODs and BOCs.

The work that needs to be completed is presented in detail below.  An attempt has been made to identify problems and propose solutions from the SCT Off-Detector Electronic perspective.

Back Of Crate (BOC (Optical Interface))

Eleven printed circuit cards have been fabricated

Commercial parts have been purchased for the cards.

One card has been loaded with commercial parts and two optical components (12 ch Rec. and 12 ch trans.).

Initial BOC Testing:

The optical command stream data appears to be OK, but a detailed investigation of the electronics needs to be made.

The optical received data path appears to be OK, but a detailed investigation of the electronics needs to be made.

The pixel specific part of the BOC needs to be tested.

The stand alone (no ROD) testing of the BOC is expected to be complete by the end of June.

Optical Components (First Taiwan Prototype):

Current Supply of Optical Components at Cambridge

Existing  1ea.  12 ch rec.  2ea. 12 ch trans.

Request   1ea.  12 ch rec. (Hope for 1-2 week delivery)

Total     2ea.              2ea.

This will allow for the loading of two minimally loaded (12 channels of transmitter and receiver per BOC) BOCs by early July. This will supply one BOC for hardware developments at Cambridge and one BOC for user evaluation the testing by the community.

Optical Components (Second Taiwan Prototype)

Changes are being made to the connector that connects the optical module to the BOC. The developers have not yet assigned pin numbers.

This prevents the design and manufacture of a simple card by Cambridge that converts the existing BOC printed circuit card module connector to the new module connector. This activity will take 5 weeks from start to finish.

Changes are being made to define how the optical connectors will be held in place. This is also related to the interlock safety needs for the optical components.

The PC board design of the final BOC can not start till this optical safety design is completed.

Optical components needed for the first 11 BOC prototype cards are detailed below:

Rec  21 = 11(12 links/card) + 7(96 links on 1 card)+ 2 spare

Tran 16 = 11(12 links/card) + 3(48 links on 1 card)+ 2 spare

These optical components are needed to satisfy the early needs of the macro assembly sights.

Printed Circuit Cards:

Eleven prototype cards have been fabricated and non-optical parts purchased. Artwork will have to be upgraded for the production BOC.

The optical module connector pin and the connector retention and interlocks will have to be worked out before the new lay out can be started.

BOC schedule and concerns.

5/29/02-7/7/02 Test existing card and load one more card.

6/19/02-7/30/02 Test of BOD, ROD and Module (see ROD part for details).

Unfortunately further schedule projection are totally dependent on design and availability of the optical components.

Realistic dates needed to give a schedule projection:

1. Definition of optical module connector and pins (effects BOC PC layout).

2. Definition of retention of optical module optical connectors (effects BOC PC layout).

3. Delivery of 21 receiver and 16 transmitter optical modules (effects user evaluation, system testing and macro assembly sight early needs).

4. Items 1-3 above will need to be completed in 2-3 month to allow for a PRR in the October time frame. This will allow for some production units available about 1/15/03

Read Out Drivers (ROD)

RODs printed circuit cards (15 ea.)have been  fabricated.

The printed circuit artwork will have to be updated.

Parts for 13 cards have been purchased.

Loading has been done to 4 cards.

Testing is underway on the RODs at LBL and Cambridge.

The boards are currently counted as production (have full functionality) boards.

VHDL(FPGA software) Changes/additions:

When a trigger appears on the serial data streams (used in calibration and diagnostic), Multiplex the event type etc. to the Event Fragment Builder Event Header FIFO.  This is used to specify event identification (by June 14th).

Implement the event counter reset and add the counter to the header (by June 14th).

Configuration and data trapping change: The data trapping in the input FIFOs shall have a delay value and number of samples to be trapped (by June 14th).

Event fragment builder change parsing of event header information (by June 14th).

Above VHDL changes needed for initial user evaluation.

Configure the Formatter FIFOs dynamically. Need to handle the event size when one of the links to a module is turned off (by July 19th).

Suppressed stuck bit in chip (causes full occupancy on a channel) data in the event fragment builder)(by July 30th).

Fix miscellaneous problems.

Printed Circuit Boards:

The 15 boards fabricated have had the layers stacked incorrectly (Ground and power layers used to shield and define impedance).  This causes additional cross talk (compensated by filtering on a few traces). The artwork will be corrected and cards fabricated (by July 30th) so that fabrication of the remaining 9 cards will be true production models.

Digital Signal Processor Software Needs:

Initial software needed to perform the initial user evaluation is shown below:

Histogram data in a slave DSP (by June 15th).

Histogram control in the master DSP(by June 15th)..

Save data from the slave DSP to crate CPU (RCC) (by June 15th).

Long Term Digital Signal Processor Software Needs:

Initialize modules from internal data structure.

Error processing in slave DSPs.

Fitting of histograms.

Etc.

User Evaluation:

It was decided to use ATLAS DAQ for user evaluation of the ROD and BOC some months ago.  It turned out the progress on the DAQ effort was slow.  This was due to a lack of manpower (lack of personnel and only part time efforts) for the DAQ and user evaluation.

A plan has been developed to perform the user evaluation on the ROD and to a lesser extent on the BOC.  The plan is to use the test stand software to evaluate the ROD and BOC combination.  The nature of the test stand is such that is can perform needed test but not in a user-friendly way. The screen are designed to test RODs not test modules and RODs. The tests are not meant to be extensive but provide clear proof that the ROD meets the basic user requirement. It is expected that the user community will be able to recommend that the ROD meet its design goals and pass the FDR (permission to build 9 more RODs). For the production readiness review the DAQ must be up and running for the extended testing of the ROD (about Oct. 2002) this is of concern.

The plan developed to test the ROD for the US ATLAS FDR is outlined below:

Configuration: Configuration uses the primitives “read_Write_Register” to configure BOC and ROD and “tran_Serial_Data” to configure front end modules. However, note the requirement to send configuration data from the ROD, as highlighted below.

Use existing primitives with software and VHDL being developed to provide triggers, then send data to host (users).

Use histogram control to histogram in the slave DSPs. Demonstration is needed to determine time used to histogram modules connected to a ROD (one or more module will be used). The most important mode corresponds to Phase 2 - histogram a burst of triggers (either from internal or external source) - basically mimic MuSTARD operation.

Phase 2A should be implemented if possible - though since

configuration changes will have to be sent from the ROD,

“tran_Serial_data” will need modifying to allow this.

Use the input FIFOs to generate events at 100kHz to the S-Link. Use a logic analyzer and event trapping of events in slave DSP to check event quality. The tests should include error events and no data on a stream (not an exclusive list!).

ROD Schedule:

5/29/02-6/15/02  Complete Initial VHDL upgrades to ROD

6/1/02-7/30/02   Upgrade ROD artwork and fabricate 10 PC boards

6/1/02-7/25/02   User evaluation with ROD test stand

7/31/02          ROD US ATLAS FDR (permission to build 9 RODs)

8/1/02?-11/1/02? User evaluation with DAQ of ROD and BOC with reviews by ATLAS FDR and PRR. (This will be hard to do with existing effort on DAQ and user evaluation.).

TIM

There are sufficient TIMs that exist or will be build to respond to the needs this year.  The final time design has not started. It may be that the TIM will not be able to participate in the PRR except as a status report.