## Slide 1: SCT and Pixel Off Detector Electronics Status April 30, 2002
<number>
Back Of Crates (BOC) Card
Current Status
BOC1 is the pre-production prototype:
    Using production compatible components
    Should move seamlessly into production
    The Connectors for the optical components will be changed for
    productiion PCB manufactured (11 ea.) - Done
Parts(commercial delivered (for 11 BOCs)
PCB manufactured (11 ea.) - Done
Have receipt of 2 TX & 3 RX Opto Plug-Ins
Hope to have more Opto Plug-Ins by June (Limited by lack of ASICs).
Testing has BOC1 has started with reading and writing of register.
Testing is expected to be completed in 6 weeks.
Concerns:
No specific concern for the ROD FDR.

## Slide 2: SCT and Pixel Off Detector Electronics Status April 30, 2002
<number>
Timing Interface Module (TIM)
Status update:
TIM is operational for user evaluation needs.
To do:
Design and fabricate production TIM (CPLDs are obsolete).
Concerns
Learning curve for FPGA implementation (just starting).
None for the FDR of ROD
Plans and schedule
Six more TIMs (iteration of prototype) to be manufactured soon for Q2
Redesign/implement TIM using new parts ("final" system) for Q3 2002.

## Slide 3: SCT and Pixel Off Detector Electronics Status April 30, 2002
<number>
Read Out Driver (ROD)
Evnt
Frg
Bldr
Fifo0
Evnt
Frg
Bldr
Fifo1
Router
Event
Fragment
Builder
DSP3
Fifo/Buffer
DSP2
Fifo/Buffer
DSP1
Fifo/Buffer
DSP0
Fifo/Buffer
DSP3
Module
DSP2
Module
DSP1
Module
DSP0
Module
Link 0DATA 1b
Link 11DATA 1b
Link 12DATA 1b
Link 23DATA 1b
Link 24DATA 1b
Link 35DATA 1b
Link 36DATA 1b
Link 47DATA 1b
Link 48DATA 1b
Link 59DATA 1b
Link 60DATA 1b
Link 71DATA 1b
Fifo 40b
DATA
Fifo 40
DATA
Fifo 40b
DATA
Fifo 40b
DATA
Fifo 40b
DATA
Fifo 40b
DATA
EvntFrgBldr
DATA 46b
EvntFrgBldr
DATA 46b
Event 46b
Header/Trailer
Events 46b
Events 32b
Trapped 32b
DATA
Trapped 32b
DATA
Trapped 32b
DATA
Trapped 32b
DATA
SLINK 1b
TIM EventDATA 16b
TIM TriggerDATA 8b
from TIM
Processed 16b
Trapped
DATA
Processed 16b
Trapped
DATA
Processed 16b
Trapped
DATA
Processed 16b
Trapped
DATA
SLINK
Event Fifo
32bx4W
SLINK
Link 72DATA 1b
Link 83DATA 1b
Link 84DATA 1b
Link 951DATA 1b
Fifo 40b
DATA
Fifo 40b
DATA
Formatter
Fifo0
Formatter
Fifo1
Formatter
Fifo2
Formatter
Fifo3
Formatter
Fifo4
Formatter
Fifo5
Formatter
Fifo6
Formatter
Fifo7
DataValid 1b
VME Bus
BOC
To Formatter
ROD Controller

## Slide 4: SCT and Pixel Off Detector Electronics Status April 30, 2002
Read Out Driver (ROD)
<number>
Read Out Driver (ROD)
Current Status
Production model RODs (4 ea.) have been fabricated.
Debugging was complete on four cards. The new memory test primitive has
uncovered SDRAM errors on Slaves 1 and 3.
Cambridge has one production model ROD for system testing.
Data Flow:
Through the Formatter, Event Fragment Builder, Router
and Slave DSP is working.
Initialization is working,
Communication is working.
DMA from router to slave DSP is being upgraded.
DMA from slave DSP to Host (RCC) is working.
VME (A32, D32) read/write to the ROD working
Running primitives in the Master/Slave DSP working.
Controller FPGA is working.
Triggering of front end modules is being upgraded with counters
(BCO etc.) and registers (event type etc.).
Configuration of front end modules is working

## Slide 5: SCT and Pixel Off Detector Electronics Status April 30, 2002
Read Out Driver (ROD)
<number>
Read Out Driver (ROD)
Read Out Driver (ROD)
Current Status (continued)
Hardware upgrades required:
VHDL to enable trapping of module configuration return data (pixels)
VHDL to provide ROD based counters of BCOs, Triggers and registers
for event type related data for stand alone operation.
VHDL for recognition of fast command on the serial data streams from the
master DSP via the controller to the front end modules.
VHDL for new Router Trapping algorithms and DMA frame format.

## Slide 6: SCT and Pixel Off Detector Electronics Status April 30, 2002
<number>
Read Out Driver (ROD)
Current Status
Test Stand Software
The test stand software will be used for the early tests at Cambridge. Will
expand this for early user evaluation. The primitive tran_serial_data will be
expanded to configure modules with user supplied serial streams.
The test stand software is about 85% complete.
The remaining software is for the production test stand.
DSP Software Status:
The DSP primitive software will allow for Module/ROD/BOC configuration,
triggering of modules and read out of events to the crate processor.
Interrupts are working with BIOS work under Texas Instruments (TI)
library 1.2.
Will grad to TI library 2.0
(note TI libraries 1.0, 1.2 and 2.0 are not compatible)

## Slide 7: SCT and Pixel Off Detector Electronics Status April 30, 2002
<number>
Read Out Driver (ROD)
Current Status
DSP Software Upgrades Needed:
Improve the DSP processing of event data so it has event boundaries
not number of word boundaries
Code histogram packages in the slave DSP
Code send data (Programmed I/O and DMA based) (slave to host)
Code calibration package
Code DMA handling packages
Projected schedule
Production Model RODs (4 ea.) have been fabricated
So far these 4 RODs will be part of the production RODs (100 ea.)
Parts and PC boards are in hand to fabricate 9 more RODS.
User evaluation from 2/02 till 5/02 is needed to have FDR of ROD.
Fabrication of 9 RODs will follow FDR.
PRR should be 8/02 for fabrication of RODs (total of 100)
Crates 8ea. will be purchased when CERN has the purchase order in place.

## Slide 8: SCT and Pixel Off Detector Electronics Status April 30, 2002
Read Out Driver (ROD)
Concerns
User evaluation is needed for the ROD to proceed to production. There
needs to be much activity in the next 2 months to keep to the schedule.
Determine the reason for external memory errors with slaves 1 and 3.
The DAQ effort is of part time personnel. This makes the prediction of a
PRR in the 8th month doubtful. In my opinion this must be changed if
the DAQ has any hope of being ready before the end of the fiscal year.
We may have to use the test stand to continue the user evaluation.
Efforts are underway to define what is needed to show that the ROD meets the
user evaluation needs of the FDR (permision to build 9 more RODs).
<number>

## Slide 9: SCT and Pixel Off Detector Electronics Status April 30, 2002
Read Out Driver (ROD)
Concerns
Current definition of evaluation needs by P. Phillips and R. Jared are shown
below:
Configuration uses primitives read_Write_Register to configure BOC and
ROD and tran_Serial_Data to configure front end modules.
Use existing primitives with software and VHDL being developed to
provide triggers, then send data to host (users).
Uses Calibration to histogram in the slave DSPs. Demonstration is needed to
determine time used to histogram modules connected to a ROD
(one or more module will be used).
Use the input FIFOs to generate events at 100kHz to the S-Link. Use logic
analyzer and event trapping of events in slave DSP to check event quality.
A meeting (P. Phillips, R. Jared and J. Hill) will be held at Abingdon UK
on May 6th to refine the definitions above.
<number>