ROD Working Schedule

John J. vacation Aug. 15 to Sept. 1.

Mark N. vacation Aug. 6 to Aug. 27.

Overall Schedule:

3 ea. Production Model cards loaded by Sept. 25.

3 ea. Cards tested at LBL by Oct. 10.

Cambridge production model card tested (partial user evaluation) by October 25.

ROD Final Design Review. Needed to meet management constrants.

7-9 RODs fabricated (5 % production) by November 30 2001.

When there is significant user evaluation the remaining ROD will be fabricated. The fabrication will take about 3 months to complete.

Production Model Board:

Schematic Update by July 17 for hand off to Brian. (Done on July 24)

New parts order to complete 12 cards plus spares by July 30. (Projected Aug. 15)

PC Board layout finished by Aug. 7 (OK)

PC Fabrication by Sept. 1  (15 ea.)

Load 3 ea. By Sept 25

Load 7-9 ea. After testing of the first three.

VHDL:

Note only the Controller is in development all other items are normal maintenance issues.

Formatter (coming out of hold ) MN 5d  (Needs test vectors complete by Aug 7)

EFB Token data format, data order JJ 5d  (Changes made, test by Aug 7)

Router OK

Program Resource Manager  JJ 1d  (Done)

Controller  FE occupancy, trailer flag and serial links MN 5d (Done)

Controller Bus bridge JJ 5d (Done)

DSP Code:

New library and code testing  LT (done)

Primitive to send serial data to front ends RJ needed in mid August

Primitive to pool busy for BOC read write RJ needed in mid August

Wiring test of ROD (needed to test production cards):  Projected by Aug. 15

Will will start testing next week (estimated 2 week job)

Test Stand Software:

Test stand software in current state can run production testing.

New effort is to optimize the production testing software.

Lukas will train Jan at Prague.

Lukas will incorporate the two need primitives into code at Prague.

Jan will come to LBL late  Sept.