Off  Detector Electronics Working Schedule

Overall Schedule:

July to October 2001

ROD Sept. 25, 3 ea. Production Model cards loaded.

ROD Oct. 10, 3 ea. Cards tested at LBL.

BOC Oct. 1, Complete layout of production model BOC. This requires the selection of vendor and foot-print of the optical components to complete layout. There is concern that the schedule could slip.

TIM  The existing TIM is suitable for testing till December.

TIM Oct. 30, Fabricate and test 2 ea (6 more can be fabricated as needed)(clock timing corrected).

TIM October 30, CLPDs 6 of 10 tested (4 of 10 tested previously).

RCC Aug. to  Oct. Initial testing of prototype DAQ-1 and comparison to ROD test stand results.

ROD, TIM and BOC Aug. to Sept.  Continued testing of updated ROD FPGA and DSP code with test stand at Cambridge.

November to December 2001

ROD November 1, Initial Cambridge production model card tested with ROD test stand.

ROD  November, Design Review. Needed to meet management constraints.

ROD November 30 2001, 7-9 RODs fabricated (5 % production). Cards needed for user evaluation, system test and macro assembly sites.

BOC Dec. 31,  3 ea. Production model BOCs loaded. This requires optical components for 3 complete cards in hand by November 30. There is concern that the schedule could slip due to the optical components.  The existing BOC cards could be used for preliminary testing.

TIM November start design of final TIM

TIM Dec. 31, Complete testing of TIM functionality at Cambridge (TCC testing schedule is not clear at this time).

RCC Dec. 31, SCT DAQ-1 ready for preliminary system test at CERN.

January to March 2002

BOC, ROD, RCC and TIM Feb. 1, Start testing at CERN (System Test)

BOC, ROD and TIM March, Complete initial testing at CERN (System Test)

SCT Off Detector Electronics Production Readiness Review April 2002 (exact date to be determined by system test result).

April to June 2002

TIM June,  Production model fabricated.

Fabrication of ROD and BOC and TIM April to September

Fabrication of TIM July to October (UCL to confirm date).