## Slide 1: SCT ROD Status
R. Jared

## Slide 2: ROD Overview
BOC
VME64X
module and BOC cont
module data
clk
Trig-info
TIM
ROD
RCC
TCC
ROS
L 2
ATLAS control, DAQ and L3 Farm
ROD
BOC
module and BOC cont
16 ea.
Module data
Module cont.
ROD output data
Slink driver
Slink driver
module data
ROD output data
48
48
96
96
96
96
Module data
L1 Trig
data
Cal.
Muon
data
cont.
cont.
cont.
SCT Off-detector Electronic Crates (1 of 8 shown)
results
configuration
status reports
errors reports
data
.
.
.
.
.
.
16 ea.
region of interest
cont.
RCC, ROD Crate Controller
TIM, Timing Interface Module
BOC, Back Of Crate card
ROD, Read Out Driver
(optical interface)
Busy
Busy

## Slide 3: SCT ROD Status
The SCT ROD PRR/FDR was passed.
Recommendation from the PRR review resulted in some changes to the ROD.
1. The slave DSPs are now on mezzanine cards.
2. The C code for histogramming has been increased in speed. It still needs SCT
testing in the UK.
3. The slave DSP memory has been increased from 32 mega bytes to 256 mega
bytes. This results in potential unification of the SCT and pixel RODs.
This unification results in a larger spare pool.
4. S-link LED has been added with new display functionality.
5. The Rev E ROD has the above functions.
The VHDL for the Rev E ROD has been been upgraded and tested with no known defects.
The C code has been upgraded and tested on the Rev E ROD at LBL.
Rev E user evaluation has not been done at this time in the UK.

## Slide 4: SCT ROD Status
Changes from the Rev C to Rev E:
Item Rev C Rev E
Slave DSP and Memory on Board on mezzanine card
Slave DSP TI 6701 TI 6713
Slave memory 32 MB 256 MB
Formatter FPGA VirtexE 400 Spartan2E 600
Formatter Output Debug Memories present removed
Event Fragment Builder VirtexE 400 Spartan2E 400
Router FPGA VirtexE 300 Spartan2E 400
Controller FPGA VirtexE 600 Spartan2E 600
Program Reset Manger FPGA VirtexE 200 Spartan2E 200
Flash Memory 12 MB 16 MB
Board Parts Loading SCT and pixel different SCT and pixel same

## Slide 5: SCT ROD Status
Rev E ROD Fabrication:
Two Rev E RODs have been fabricated and debugged.
25 Mezzanine cards have been fabricated. Byte addresses were incorrect. Four wires are being added to each card.
Aug 27-Oct 6 Fabrication of 100 DSP mezzanine cards
Aug 27-Sep 17 Purchase parts for 100 Mezzanine cards
Aug 27-Sep 26 Fabrication of 25 ROD PC cards
Sep 29 Permission from the user community to continue with ROD parts loading
Sep 29-Oct 10 Load 23 ROD PC cards
Oct 6-Oct 23 Load 100 mezzanine PC cards
Oct 17 4 Rev E cards debugged
Nov 15 23 Rev E cards debugged

## Slide 6: SCT ROD Status
ROD Distribution:
Current:
UK 3 Rev B, 5 Rev C 1 Rev E
Pixel 1 Rev B, 4 Rev C 1 Rev E
Wisc 0 Rev B, 1 Rev C 0 Rev E
Oct 17:
Rev E 2->UK, 2->P
Rev C 2P -> 2UK
UK 3 Rev B, 7 Rev C 3 Rev E
Pixel 1 Rev B, 2 Rev C 3 Rev E
Wisc 0 Rev B, 1 Rev C 0 Rev E
Nov 15:
Rev E 10->UK, 3->Wisc, 6->P
Rev C 2P->UK
UK 3 Rev B, 9 Rev C 13 Rev E
Pixel 1 Rev B, 0 Rev C 9 Rev E
Wisc 0 Rev B, 1 Rev C 3 Rev E

## Slide 7: SCT ROD Status
Concerns:
Some SCT user evaluation is needed by the end of September to proceed with confidence the loading of 23 Rev E RODs.
The Pixel PRR is scheduled for October 27. This leaves little time to perform a pixel user evaluation.