Discussion on the evolution of the MVD system tests, towards the full test and the installation of the MVD in ZEUS (2 Aug 2000)

In a round table meeting we tried to specify the various steps needed to arrive to a full MVD system test. We discussed which is the hardware required and a rough schedule (mostly dictated by hardware availability). We did not discuss the names of people involved, even if there is already some effort to specify a list of person associated with each task. We also did not went into the details of what software is needed at every stage: for the readout and slow control this seems to be well understood by the experts, maybe some clarification is needed on the data quality monitoring.  The foreseen major steps are:

- Single channel test

- Ladder test

- Full system test

- Installation test

## Single channel test

The system is presently setup to readout one single channel, expandable to two, with prototypes of all the final electronics. Foreseen upgrades:

- Prototype of the final analog link card (Nikhef, Aug 7). This card will provide 8 channels input to the ADC. 15 ADC modules already present in DESY. To be fully tested before Katsuo leaves (Aug 21).

- Cleanup of the C&C patchbox card (Gil Nixon, Aug 7 till 10). Wiring cleanup and new LV supply.

- Use of a ½ module instead of a single hybrid. Need a bias supply. Possible now, modules available.

- Use of the final LV and HV systems. Need slow control system (CAN). Possible from September.

- Readout a full module (2 hybrids) on one channel. Useful to see signal quality. Possible second half of August,  need technical help to build the module on a support frame.

- Use of a source and a PMT-scintillator. Dates TBD

The single channel test will provide already the opportunity to make different run types (pedestals, test pulse, external trigger) and to run the ADC in different modes (full data, pedestal subtraction, sparsified readout with zero skipping and clustering)

#### Ladder test

One ladder with “B1” type hybrids will be available within September. The production of the detectors from the new batch has already started. The ladder will be used first at Nikhef for test cabling. The readout of one ladder needs the prototype patchbox and one final prototype for the C&C helix interface. Both are planned to be ready Oct 15.  Plans:

- First ½ of October: move the test setup to Jade hall.

- Second ½ of October: cable the ladder to HV, C&C, LV and start to check the signals.

  - NOTICE: at this stage the final cables from the patchbox to the racks are needed (at least for 5 channels).

  - To keep a whole ladder powered for a long time, we need cooling of the hybrids, so the cooling system has to be connected and tested.

- November: test in details the performances: IV curves, noise, DAQ and Slow control, also with the cosmic trigger.

  - The trigger telescope, to be used in the MVD system test, has to be ready at this point.

  - Data quality monitor software is needed at this stage

##### System test

The MVD is foreseen to arrive in Jade hall in November. Plans for the system test:

- After arrival, test of each single ladder and wheel of the MVD (<1 week), using the ladder test setup.

- Open MVD, install beam pipe, close MVD.

- Test again all modules.

- Build up the full system, as soon as the complete patchboxes arrive (December) and test the signal quality (cross talks, ringing, grounding problems) and system stability (temperature, IV etc.)

  - Needed all the cables from PB to crates (and experts to do the work).

- Test with cosmic trigger (January).

  - Extensive data quality monitor and event display needed.

  - Contact with MVD offline group needed to be prepared for track reconstruction (event data format, geometry etc)

- Move MVD to ZEUS.

- Fast test of all modules before the final cabling.

  - Build a single ladder (or single module?) test system in the Zeus hall while installing MVD

##### Other issues

- A test of a multicrate readout system (with fast ethernet connection) is foreseen in November.

- There is no plan for an SLT test in the MVD system test.