## Slide 1: ABCN 130 nm Discussion
Overview of the list of activities toward a first version of ABCN in 130nm
Slides for specific domains (in black) :
  Front-End
  RAM design
  Data and Command format
  DCDC implementation
The way to progress (milestones etc…)

## Slide 2: ABCN 130 nm Discussion
End 2010
Mid 2011
End 2011
Obtain Protos
FE design
DC/DC and SP
SEU Logic
Obtain
RAM block
Submission
Protos
results
ABCN full verilog code
Mid 2012
RAM SEU
test
FE specs
Data format specs
TESTS
DESIGN

## Slide 3: ABCN 130 nm Design Tasks
Element | Work 1 | Institute/person | Time period | Condition
FE redesign | Redesign | Jan | Q2 2011 | According to specs
FE Bias/DAC & layout | Bias/DAC & layout | Jan + ? | Q3 2011 | 
RAM blocks | RAM generator | CERN/ME | Q3 2011 | 
RAM blocks | test |  | Q3 2011 | SEU test
RAM control | Verilog code | Francis | Q3 2011 | 
Command Decoder | Verilog code | Francis | Q3 2011 | 
Data Compression Logic | Verilog code | Daniel/Geneva | Q3 2011 | 
Readout Logic | Verilog code |  | Q4 2011 | 
Verilog code | Verilog code |  | Q1 2012 | + 3 months min

## Slide 4: ABCN 130 nm Design Tasks
Element | Work 1 | Institute/person | Time period | Condition
I/O parameters | Spice simulation + bidirectional design | Mitch/PENN |  | 
Readout data format | Specification | Strips readout group | End March 2011 | Include L0/L1 preview Y Freeze at Oxford AUW
CD data format | Specification | Strips readout group | End March 2011 | Include L0/L1 preview Y Freeze at Oxford AUW
All digital | P&R | Krakow/CERN | 1st semester 2012 | Krzysztof + ?
Final chip | layout assembly | Krakow/CERN | 1st semester 2012 | Krzysztof + ?

## Slide 5: ABCN 130 nm : Module Controller Chip
Element | Work 1 | Institute/person | Time period | Condition
MCC | Verilog model |  |  | To check with the ABCN data format definition
MCC | Specification/Design | PENN |  | Compatibility to GBT

## Slide 6: ABCN 130 nm :
Gain 100mV/fC
Linear range 4fC (saturation at 6fC)
Peaking time 22ns
Current consumption of the front end channel; Iinput+80uA (Iinput = 100-160uA)
Power consumption (1.2V supply); 220 – 290uW / channel
130nm Front-end (J. Kaplon)

## Slide 7: ABCN 130 nm :
Channel 22um x 700um
Chip width;
  channels; 256 x 22um = 5.6mm
  bias + decoupling; 500um
  Pads; 600um
  DACs + bandgap; 500um?
  Total; 7.2mm  two questions to module:
    Is it OK?
    How much we can increase (if necessary) this number?
130nm Front-end (J. Kaplon)

## Slide 8: ABCN 130 nm :
130nm Front-end (Barrel layout proposal, UK, Geneva, KEK)
Max width 7.5 mm
Would like only FE on top edge
Data, clock, command on sides
  Maximizing spacing between pairs, no redunancy
Ground, power and chip ID on bottom
7.5 mm
FE bonds only (4 rows of 64)
Token and Data (2 pairs)
Token and Data (2 pairs)
BCO, L1, Com, Clk, Reset (5 pairs)
Ground, Power, Chip ID

## Slide 9: ABCN 130 nm :
130nm Front-end (Barrel layout proposal, UK, Geneva, KEK)
Would like FE bond pads to take full width of ASIC
  Ground pads if needed below FE connections
    Ground pads would have to bond to the side, use same pad shape as for BE
Would like ~50x200 mm pads with 100 mm spacing between rows
200 mm
100 mm
Ground (if needed)
1100 mm

## Slide 10: ABCN 130 nm : RAM
RAM cell (2.2x2.5um2) and RAM generator design work is currently started in PH/ME (C. Paillard + student, not specific to ATLAS)
Best case availability : Summer 2011, 256x256 block
1st version does not include ECC (ECC may be needed for long latency time as in L0/L1 architecture)
Support from experiments welcome for TID/SEU radiation tests (Summer 2011) Availability best case : Summer 2011
We will build regular contacts with PH/ME to understand specifications and progress, tests to be carried on

## Slide 11: ABCN 130 nm : Digital Functions
(Missing) one person for building the code for the new readout part
(Missing) one person for building the code for the L0/L1 inclusion
Specifications of readout and commands formats should be completed soon  should include L0/L1 format requirements
Aim is to have a complete chip verilog description Q1 2012
Covers HDL description for RAM control, DCL, Readout
Data format specifications should be frozen at end of March 2011 (AUW)

## Slide 12: ABCN 130 nm : Digital Functions
Header
Data
N Fixed size data packet
1 chip
Header
Data
Header
Data
Next chip
No need of Data concat. Btw. chips | No Constraint btw.chips
Multiply nbe of headers | Occupies BW

## Slide 13: ABCN 130 nm : Digital Functions
L01
L02
R31
R32
L11
L12
L0ID1
L0ID2
Fixed Latency
No fixed Latency
Time ID
Geographical ID
0.4-1MHz rate
40-100KHz rate
Ty
pe
L0ID
Event
ERC
L0 or L1 or Control Data or DCS Data
Trigger command with L0/L1 capability
Data content with L0/L1 capability

## Slide 14: ABCN 130 nm : Digital Functions
Additional time estimated for L0/L1 : + 3 months at best (depending on complexity and availability of RAM generator)
L0ID
Mem
Pipeline
L1 buffer (AddressableMemory)
DCL
SER
RR
ROL
BC
WA
RA
WA
RA
PE
@L0: RA=WA-Nlat
WAcalc
RAcalc
@BC : WA=WA+1
R3 latency (3us ?)
L1 latency and Event Buffer
L0
Match
L0ID
W
L0ID gen
R
L1
R3
L0
Mem
W
R
L0
Missing resource
Missing resource

## Slide 15: ABCN 130 nm : Module Controller
The verilog code of the MC (FPGA, ASIC) should be build at the same time as the readout code is written for ABCN130 to verify data transmission compatibility
Also the compatibility with the GBT E-link has to be defined and verified (clock in & clock out frequencies, etc …)

## Slide 16
Decisions Procedure
Specifications for Front-End (detector segmentation & hybrid experts) : Target AUW 2011.
Specification for CD and Data Format : Strips Architecture working group. Target AUW 2011.

## Slide 17
Milestones
End 2010
Mid 2011
End 2011
Obtain Protos
FE design
DC/DC and SP
SEU Logic
Obtain
RAM block
Submission
Protos
results
ABCN full verilog code
Mid 2012
RAM SEU
test
FE specs
Data format specs
TESTS
DESIGN

## Slide 18
Resources Issue
Missing resources :
One digital designer for the readout part of ABCN 130
One digital designer for the L0/L1 implementation
One part time effort for MCC specifications fixing

## Slide 19
Backup Slides

## Slide 20: ABCN 130 nm : Where we are
  VDD = 1.9 V
  VOUT = 926 mV
  IOUT = 60 mA
  CX = 1000 nF
  CL = 200 nF
  f = 1 MHz
M1 (PFET)
28.2mm / 0.24μm
M2 (NFET)
18.0mm / 0.30μm
M3 (NFET)
18.0mm / 0.30μm
M4 (NFET)
6.0mm / 0.30μm
M1 Buffer
M2 Buffer
M3 Buffer
M4 Buffer
Clock Gen
Power
Efficiency
= 97%
(including all circuitry)
Step-up converter design
M. Bochenek

## Slide 21: ABCN 130 nm : Where we are
21
M1 (NFET)
980μm / 0.24μm
M2 (NFET)
980μm / 0.24μm
M4 (PFET)
2000μm / 0.24μm
M3 (PFET)
2000μm / 0.24μm
Clock Generator
Level
Shifter
Level
Shifter
Buffer 2
Buffer 1
  VDD = 0.9 V CPUMP = 470 nF
  VOUT = 1.55 V CLOAD = 470 nF
  IOUT = 32 mA f = 500 kHz
Total area = 0.04 mm2
(200 x 190 μm2)
Power
Efficiency
= 85%
(including all circuitry)
Step-up converter design
M. Bochenek

## Slide 22: ABCN 130 nm : Where we are (status)
SEU Logic test
Slow Command
decoder
Fast Command
decoder
Serial Register
xx-SEU (4 bits, static)
yy-SEU (7 bits, static)
Serial Out
yy-REGSEU (7 bits, one clk)
RTL exists
SEU Logic part
(F. Anghinolfi,
K. Swientek)
SPP Elements
(M. Newcomer,
N. Dressnandt)

## Slide 23: ABCN 130 nm Discussion
Techno: stick to 130nm
256 channels, one sided
Analogue : test of the front-end to be done as soon as it is back (December)
L0: could be skipped for first 130nm version
Radiation hardness: should be implemented
Memory: need to find a good memory block. The one from IBM is not rad hard. Mitch to discuss with a US company. Effort started at CERN PH/ME.
Switched capacitor DC-DC: it should be possible to use the block (prototype block expected in December for tests)
Serial power : elements (shunt transistor) should be implemented
Readout data format: fixed length to be implemented as it is the simplest and that with the new luminosity target it's very likely to be good enough

## Slide 24: ABCN-130 : number of channels
FE pads
4 rows
1mm x 10.0mm
256 FE channels
Width : 0.7mm
Height : 10.0mm
(7.2 mm min)
22um pitch
Max digital
area
2mm x 10.0mm
10.0mm
(7.2mm min)
4.0mm
256
ABCN 25
Size (same scale)
7.7mm
7.5mm

## Slide 25
WE SHOULD ALLOW OPERATION WITH DIGITAL VOLTAGE RANGE FROM 1.5V TO 0.9V (for Lite, incl. on hybrids)
Lite ABCN-130 Powering
This is justified by :
  The SEU cross section is strongly depending on the VDD of registers
  The standard cells characterisations are valid from … to … (not know now)
  Power consumption optimization vs. other parameters (frequency, voltage margin, digital noise, total dose)
WE SHOULD EVALUATE HOW THIS CONSTRAINT IS AFFECTING THE SERIAL OR DC/DC POWER DISTRIBUTION developments during the prototype phase

## Slide 26
256 channel ABCN-130 Powering (Low VDDD)
DC/DC
DC-DC
DC/DC
LDO
Serial
Power 1
2.4V
1.8V
Shunt
Serial
Power 2
Shunt
DC/DC
1.2V
0.9V
1.2V Analogue (45mA)
0.9V Digital (102mA)
0.9V Digital (102mA)
Analogue (45mA)
Digital (102mA)
1.2V Analogue (45mA)

## Slide 27
256 channel ABCN-130 Powering (Std VDDD)
DC/DC
DC-DC
DC/DC
2.4V
Serial
Power
Shunt
1.2V
1.2V Analogue (45mA)
1.2V Digital (102mA)
1.2V Digital (102mA)
1.2V Analogue (45mA)
Even in the case of “one source” for analogue and digital, remains the issue of using LDO for analogue power quality

## Slide 28
ABCN-130 Data Transmission
Basically 2 mechanisms were under discussion :
Data packets built with data from adjacent chips (data concatenation constraints as for ABCD)
Independent Data packets (per chip, each packet contains its full identifiers) (impact on BW, compatibility with track trigger data, …)
Assumption : due to reduced BW requirement (to be proven) the last schema becomes preferable

## Slide 29
Data packets built with data from adjacent chips :
  With Token (as ABCN now) : timing constraint, workable in 130nm
  Xon/Xoff : no token timing constraint, one FIFO and some add. Logic in each chip
ABCN-130 Data Transmission
FEI
FEI
tk
data
FEI
FEI
WE
data
There are 2 variants, one does not requires WE at each chip (see backup slide)

## Slide 30
We may use a simple Xon/Xoff mechanism in case of independent data packets (not dependancy on exact chip to chip timing)
The track trigger readout priority is also in favor of the “short” independent data packets method
ABCN-130 Data Transmission

## Slide 31
In ABCN-25 the redundancy has resulted in :
  Adoption of a Bidirectional data flow from chip-to chip (affects only the I/O circuits, very little impact on logic) that I believe we should maintain (free to transmit data either side of a chip to its neighbour or MC)
  Dual clock and COM inputs
  The main impact is for hybrid design (carry dual clock and COM lines along hybrid)
ABCN-130 REDUNDANCY

## Slide 32
Schedule
Full description of the (Lite) chip(s) mid of 2011
Floorplan and layout for submission in period in period Q1-Q2 2012
Schedule subject to commitments, should be assessed soon, (also in conjunction with the MC design ?)

## Slide 33
Schedule
May 2010
Mid 2011
Mid 2012
Now
FE design
DC/DC and
Regulators
SEU structures
I/Os, DCS ?
Partial HDL code
(ABCN, MC ?)
Submission
(ABCN, MC ?)
Test results
RAM block

## Slide 34
Cost estimate and resources
The projected MPW submission cost is around 30KUSD (3KUSD/mm2)
One Engineering run in 130nm is 405KUSD (2 wafers) + 3.6KUSD/wafer
Cost
Resources (manpower)
We should assess them (organisation/institutes) :
Seeking young people
List tasks and distribute
Select appropriate software tools
Organize a dedicated seminar ? (Organization of design team, incl. MCC?)

## Slide 35
ABCN 130nm Open Issues
1. Define precisely design resources for 2 next years
Organize a dedicated seminar ? (Specifications, organization of design team, list of tasks)
2. On design elements :
Clarify implementation of blocks for powering
CRITICAL  RAM block development (1 year time frame)
Agreement on readout schema
Simultaneous development of MCC (with interface to GBT) ?
Rad & SEU tolerance